## Tabelle1
Risikoanalyse PiPossible
Risk | Desciprion | Prob of Occurrence | Damage | Mitigation Strategy | Person in Charge | Risk Factor
Actual Environment | RL Hardware assebeling not possible as whole team | 100 | just oneperson can assembel | one Person assembeling, the others support via VideoCall | Pascal | 1
| failure of Hardware can be complicaded to repair | 50 | more time passes until the HW arrives | order as early as Possible | Adrian | 7
Organizatial Environment | Goals are to high for the short time | 50 | Project will not be finished | Timemanagement | Adrian | 4
| Project to complex for the shortend semester | 50 | Project will not be finished in time | Timemanagement | Pascal | 2
| Projects of other subjects are more important | 50 | less time to work on this project | Timemanagement | Adrian, Pascal, Niklas | 4
| High level of technik complexity | 75 | more time to get used to the technik | Training | Adrian, Pascal, Niklas | 5
Tool failure | Used softwaretools fail | 10 | loss of Data | Backups | Niklas | 6
Requirements | Continually changing requirements | 65 | to much goals to achhiev all | weekly meetings | Pascal | 3
| System requirements not adequatly defined | 50 | implementation does not match the requirements | weekly meetings | Niklas | 4
Team | Inexperience team members | 75 | more time to achhiev goals | Training | Adrian, Pascal, Niklas | 2
| Team members lack of specialized skills | 75 | more time to achhiev goals | Training | Adrian, Pascal, Niklas | 2